## Global Plan
Phase | Timing | Audience | Objective | Key message | Channel | Owner | Status
Pre-launch | T-3 weeks | All employees | Create awareness | Your voice matters | Email (HQ) | HQ | Not started
Pre-launch | T-3 weeks | Work councils | Secure project objectives | We are planning the project to take action | Meeting | HQ + Local | Not started
Pre-launch | T-2 weeks | Managers | Prepare relay | Managers play a key role | Manager briefing | HQ + Local | Not started
Pre-launch | T-2 weeks | Leadership | Ensure sponsorship | Leadership endorsement | Email / meeting | HQ | Not started
Pre-launch | T-1 week | All employees | Build trust | Confidential & anonymous | Email / intranet | Local | Not started
Launch | Day 1 | All employees | Drive participation | The survey is now open | Email + leadership | HQ + Local | Not started
Launch | Day 1 | Managers | Activate relay | Encourage your team | Manager message | Local | Not started
During | Mid survey | All employees | Boost participation | We count on your feedback | Email reminder | Local | Not started
During | Mid survey | Managers | Activate teams | Please remind your teams | Manager relay | Local | Not started
Closing | Last days | All employees | Final push | Last chance to participate | Email | Local | Not started
Post | After closing | All employees | Close the loop | Thank you for your feedback | Email | HQ | Not started

## Feuil1
COUNTRY | COMMUNICATION PLAN | COUNCILS AWARE | LAUNCH MESSAGE | REMINDERS READY | MANAGERS ACTIVATED | LOCAL ADAPTATION READY | GO / NO GO | COMMENTS
| Not ready | Partial | Partial |  |  |  | 🟢 GO
🟢 GO
🟢 GO
🟢 GO